## Sheet1
GOAL | Milestone | Task | Time (Hours) | Assigned Team (Me) | Track Process | Start Date | End Date
Deploy BARQ Lite efficiently
Requirements Gathering &Planning
|  | Understanding Task | 2 |  | Done | Thursday (10:00) | Thursday (22:00)
Create Web App
|  | Java web app & Jar | 0.5 |  | Done | Thursday (10:00) | Thursday (22:30)
|  | Dockerfile | 0.25 |  | Done | Thursday (10:00) | Thursday (23:00)
Log rotation
|  | Write Log rotation Script | 1 |  | Done | Thursday (10:00) | Friday (1:00)
|  | Test Script | 0.5 |  | Done | Thursday (10:00) | Friday (1:30)
TLS Certificate Report
|  | Write TLS Certificate Script | 1 |  | Done | Thursday (10:00) | Friday (3:00)
|  | Test Script | 0.5 |  | Done | Thursday (10:00) | Friday (3:30)
Create Two VM on Azure
|  | Create Vms | 0.5 |  | Done | Thursday (10:00) | Friday (10:30)
Create Ansible Roles
|  | Files and Certificates role | 1 |  | Done | Thursday (10:00) | Friday (15:00)
|  | date_setup role | 0.25 |  | Done | Thursday (10:00) | Friday (15:30)
|  | App and service Setup role | 1 |  | Done | Thursday (10:00) | Friday (17:00)
|  | Docker Setup Role | 0.5 |  | Done | Thursday (10:00) | Friday (17:30)
|  | log_rotation role | 0.25 |  | Done | Thursday (10:00) | Friday (18:00)
|  | Certificate_Check role | 0.25 |  | Done | Thursday (10:00) | Friday (18:15)
Documentation
|  | Create README.md | 1 |  | Done | Thursday (10:00) | Saturday (17:00)
Create Repository
|  | Publish Solution | 0.25 |  | Done | Thursday (10:00) | Saturday (17:30)
Check System
|  | Check VMs | 2 |  | Done | Thursday (10:00) | Saturday (16:00)